## OwnerOnlyProjInfo
2.3 COST PROPOSAL
PROJECT INFORMATION FOR OWNER'S INPUT ONLY
Project Title, SBC No.: | UTM New Residence Hall UT No. 999/011-104-2024
GMP Target: | 40200000
Contract Time: | 24 | Months
.
Close-Out Time: | 3 | Months
.
Liquadated Damages: | 2000 | Per Day

## PreConFee-HrlyRates
2.3 COST PROPOSAL
Project Title, SBC No.: | UTM New Residence Hall UT No. 999/011-104-2024
A. PRE-CONSTRUCTION PHASE SERVICES (PCPS) LUMP SUM FEE
PROPOSER NAME: | Enter name in section A. Names required elsewhere will be filled in.
The PCPS lump sum fee shall be for delivery of PCPS for this Project as defined by Section 1.7, Scope of Services. The proposed amount will be used as a start point for negotiating the fee prior to the MC execution. This fee should not include costs of printing the Designer’s design/construction documents, geotechnical investigations, or property surveys during the PCPS. This fee will be paid upon successful completion of services and is not to be included as a part of the CM/GC construction services Guaranteed Maximum Price. Hourly rates are for reference and utilization in negotiating the fee.
| PCPS Lump Sum Fee | 0
Names (15 or fewer) | PCPS Job Title and/or Duties | Hourly Rate
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note to Proposers: | Enter information only in green highlighted cells.

## FixedFee-BudgGuide
2.3 COST PROPOSAL
Project Title, SBC No.: | UTM New Residence Hall UT No. 999/011-104-2024
B. CM/GC CONSTRUCTION SERVICES FIXED FEE
The proposed cost for the CM/GC construction services fixed fee shall be for providing the construction services defined by Section 1.7, Scope of Services, for the Contract Time and Project Close-Out. The Fee shall be stated as a percentage of the Project construction cost that includes the following:
1. General company overhead and profit.
2. Personnel not directly assigned to the Project such as accountants, clerks, secretaries and personnel other than those listed under General Conditions.
3. Company officers and other personnel with supervisory status not listed under General Conditions.
4. The cost of main office equipment and related supplies, maintenance, and service not located on site.
This percentage rate may be used for other services requested by the Owner.
CM/GC Construction Services Fixed Fee Percentage Based on the GMP Target |  | 0%
C. CM/GC CONSTRUCTION SERVICES GENERAL CONDITIONS BUDGET GUIDE
Labor Burden Multiplier, Not to Exceed 39%
By submitting a Cost Proposal, Proposer confirms that Proposer’s Direct Personnel Expense will not exceed the amounts set forth in A201 Section 7.3.4.2.1.
Contract Bond Rate Percentage Based on the GMP Target |  | 0%
Note to Proposers: | Enter information only in green highlighted cells

## GenCondsContrTime
D. GENERAL CONDITIONS FOR CONTRACT TIME
Project Title, SBC No.: |  | UTM New Residence Hall UT No. 999/011-104-2024
PROPOSER NAME: |  | Enter name in section A. Names required elsewhere will be filled in.
Provide costs for General Conditions including, but not limited to, the following items during the Construction Services Phase (Contract Time). CM/GC may indicate some of these items as not applicable and may also identify additional items. These costs may be clarified prior to an agreed to GMP. Actual cost records of General Condition items may be requested as a part of the final accounting at project completion to certify total actual costs. CM/GC is to base the calculation of the monthly General Conditions charge on the preliminary schedule information provided in this RFP.
Item Description |  |  | Unit | Lump Sum Cost | Monthly Cost
Total monthly cost, including labor burden, of personnel designated in Section 2.3, B.6 of the Technical Proposal that are to be included in this Cost Proposal. |  |  | Mo |  | 0
Total monthly cost for the following: |  |  | Mo |  | 0
Temporary Office Trailer(s)
Phones and Communication Devices
Pickup Truck(s)
Auto(s)
Fuel
Office Furniture and Equipment (copier, computer, fax, etc.)
Supplies & Expenses
Insurance as required by the RFP Standard Documents, based on the GMP Target. |  |  | LS | 0
Gross Receipt Tax (for this project) |  |  | LS | 0
Total for project sign, other signage, and miscellaneous CM/GC printing (not including printing of design/construction documents). |  |  | LS | 0
TOTALS |  |  |  | 0 | 0
Note 1 | Item quantities are as required for the services required by the RFP and the scope of the Project
Note 2 | Employee parking at the project site, if available, will be at no cost. The cost, if any, for additional parking will be negotiated prior to establishing the GMP.
List, for reference, the CM/GC's subcontractor default insurance (SDI) rate that may be applied to the total value of project subcontracts. If the CM/GC will not have SDI then show as "NA". |  |  |  |  | 0%
List, for reference, the estimated potential cost of known temporary construction items. Provide an explanation of costs below. |  |  |  |  | 0
| Note to Proposers: | Enter information only in green highlighted cells.

## GenCondsCloseOut
E. GENERAL CONDITIONS FOR CONSTRUCTION CLOSE-OUT
Project Title, SBC No.: |  | UTM New Residence Hall UT No. 999/011-104-2024
PROPOSER NAME: |  | Enter name in section A. Names required elsewhere will be filled in.
Provide costs for General Conditions including, but not limited to, the following items during the Construction Close-Out. CM/GC may indicate some of these items as not applicable and may also identify additional items. These costs may be clarified prior to an agreed to GMP. Actual cost records of General Condition items may be requested as a part of the final accounting at project completion to certify total actual costs. CM/GC is to base the calculation of the monthly General Conditions charge on the preliminary schedule information provided in this RFP.
Item Description |  |  | Unit | Monthly Cost
Total monthly cost, including labor burden, of personnel designated in Section 2.3, B.6 of the Technical Proposal that are to be included in this Cost Proposal. |  |  | Mo | 0
Total monthly cost for the following: |  |  | Mo | 0
Temporary Office Trailer(s)
Phones and Communication Devices
Pickup Truck(s)
Auto(s)
Fuel
Office Furniture and Equipment (copier, computer, fax, etc.)
Supplies & Expenses
TOTAL |  |  |  | 0
Note 1 | Item quantities are as required for the services required by the RFP and the scope of the Project
Note 2 | Employee parking at the project site, if available, will be at no cost. The cost, if any, for additional parking will be negotiated prior to establishing the GMP.
| Note to Proposers: | Enter information only in green highlighted cells.

## Summary
F. SUMMARY
Project Title, SBC No.: |  | UTM New Residence Hall UT No. 999/011-104-2024
PROPOSER NAME: |  | Enter name in section A. Names required elsewhere will be filled in.
Signature and Date:
The signatory must be an individual or a company officer empowered to contractually bind the Proposer.
The proposed cost and the submitted Technical Proposal associated with this cost shall remain valid for at least 60 days subsequent to the date of the Cost Proposal opening and thereafter in accordance with a resulting contract between the Proposer and the Owner.
1. | Construction Services Fixed Fee and Contract Bond
|  | Fixed Fee Percentage: | 0%
|  | Contract Bond Percentage: | 0%
|  | Total Percentage: | 0% | X | 40200000 |  | 0
2. | Construction Services General Conditions Budget
|  | Lump Sum Items: |  |  |  |  | 0
Monthly Cost
|  | Contract Time: | 0 | X | 24 | Months | 0
Monthly Cost
|  | Close-Out: | 0 | X | 3 | Months | 0
[6 empty] | TOTAL | 0